## Consolidated Schedule
UID | Task | Duration | Predecessors
1 | Phase 1: Foundation | —
2 | Define AI vision, strategic objectives and roadmap | 4
3 | Assess data quality and technology readiness | 5
4 | Establish AI governance, ethics principles and baseline controls | 5
5 | Identify key AI risks and establish initial risk register | 4
6 | Assess organisational readiness and launch awareness/upskilling | 5
7 | Select and prioritise pilot use cases | 3 | 2
8 | Complete AIM readiness assessment and establish maturity baseline | 5 | 3
9 | Phase 1 completion: foundation validated | 0 | 4,5,6,7,8
10 | Phase 2: Pilot and Proof | — | 9
11 | Prepare pilot data pipelines and infrastructure | 8 | 3,9
12 | Assess pilot risks and implement governance, fairness and explainability controls | 6 | 4,5,9
13 | Train pilot teams and prepare change support | 5 | 6,9
14 | Execute and iterate priority AI pilots | 15 | 7,11,12,13
15 | Integrate AIM into pilots and establish KPI reporting | 8 | 8,14
16 | Phase 2 completion: pilots and measurement validated | 0 | 12,14,15
17 | Phase 3: Scale | — | 16
18 | Integrate enterprise data/platform capabilities and scale model deployment | 15 | 11,16
19 | Embed automated monitoring, audit trails and enterprise risk controls | 10 | 12,16,18
20 | Expand workforce capability and adapt roles/operating models | 12 | 13,16
21 | Scale validated AI use cases across functions | 20 | 18,19,20
22 | Extend AIM measurement and governance across the AI portfolio | 12 | 15,19,21
23 | Phase 3 completion: scaled operations validated | 0 | 19,20,21,22
24 | Phase 4: Continuous Optimization | — | 23
25 | Establish ongoing model, data, technology and performance monitoring | 8 | 18,23
26 | Run periodic governance, compliance, risk and external benchmark reviews | 8 | 19,23
27 | Continue workforce learning and improve adoption practices | 7 | 20,23
28 | Use KPI results and feedback to optimise scaled AI use cases | 12 | 21,22,25,26,27
29 | Refine AI strategy, portfolio priorities and AIM measurement | 8 | 22,26,28
30 | Phase 4 completion: continuous improvement operating | 0 | 25,26,27,28,29

## License & Attribution
Intellectual Property and Licence
AIM (AI Impact and Momentum) is the intellectual property of Suhas Dutta. This material is licensed under the Creative Commons Attribution 4.0 International (CC BY 4.0) licence.
You may share and adapt this material, including for commercial purposes, subject to the licence terms. Appropriate attribution must be provided, a link to the licence included, and changes identified where applicable.
Licence: https://creativecommons.org/licenses/by/4.0/
This licence applies to this material only. It does not transfer ownership of AIM or grant rights to use AIM branding, logos or trademarks in a manner that implies endorsement. Additional AIM materials and services may be available through 3nayan at https://3nayan.in/.